Addendum - Phase 2a RFP Questions/Answers

1. What is the scaffolding plan? 
	Answer:  We have a plan in place to use a combination of scaffolding and 2 lifts. The scaffolding will allow access for the mural work above the entrance, above the organ (areas where the organ vents are located), and covering left and right mezzanine areas that can’t be easily accessed. The proscenium will be accessed with the lifts. This plan was developed after consulting with EverGreene during their site visit. The scaffolding cost will be paid by the owner and the plan may be revised upon request by the successful bidder.

2. Do you plan to do the work in phases? If so, what are you expecting?
	Answer:   We expect the design and actual work to be completed in the December to March timeframe. The timeline for the East Stairwell and Vestibule (Add. Alt. 2) will be addressed with the successful bidder if the Owner chooses to proceed.

3. What is your proposed schedule? 
	Answer:  The RFP has an Award Date of October 7, 2026 and an On-site start of January 2027. We are hoping for a 3-4 month onsite schedule. The RFP asks bidders to propose a timeline for each phase (Design development and approvals, Mobilization and lead time, On-site production, and Punch list and closeout).

1. It was mentioned that January and March have no shows, but February has a show. What is the schedule for the February show? 
	Answer:  The show will run February 14-28, weekends only, but we intend to install the scaffolding in a manner that will allow public access for the show on weekends when workers are not present.

1. I would like to confirm that the proscenium arch is not included in the scope of work. Except for the small plaster repair in the lower right-hand corner? 
	Answer: The proscenium is to be included and will be accessed via lifts as stated in the answer to question 1 above.

1. I would also like to confirm that the apron of the stage is not included in the scope of work. 	
	Answer:  Correct, the apron is not included.

1. Do you have any preliminary thoughts on what you would like the murals to be? We can absolutely do our own research and provide you with some ideas, but I wanted to see if you had any preliminary thoughts.
	Answer:  Please do your own research and provide design concepts to be approved by the Building Committee.



1. Would you like the underside of the mezzanine to be straight painted straight, or would you like decorative painting/stenciling? 
	Answer:  Provide design concepts to be considered and approved by the Building Committee. Our preference is for decorative painting/stenciling.

1. I believe you mentioned there was a high-resolution historic image; could you please send me that? The previous photos I received were lower resolution. 
	Answer:  The image has been uploaded to a Google Drive and the link has been provided to all prospective bidders.

1. Is the wainscot included in the RFP?
	Answer:  From RFP Section C-7:  “Wainscot and cap rail: base color with tinted varnish/topcoat system at beadboard panels and trim.”

1. Paragraph 18 of the Terms and Conditions states that "Liquidated damages in an amount per day will be specified by the Owner." Can you specify what that amount is? 
[bookmark: _GoBack]Answer:  If the Contractor fails to achieve Substantial Completion from thirty (30) days following the Substantial Completion Date (the “Outside Completion Date”) then the Owner shall be entitled to recover from the Contractor an amount equal to one hundred and 00/100 Dollars ($100.00) multiplied by the number of days from the Outside Completion Date to and including the date that the Contractor achieves Substantial Completion provided such delay is solely attributable to the Contractor and there are no concurrent days attributable to the Owner or any third party. This will be further codified in the Contract with the successful bidder.

1. Will retainage be required and, if so, in what amount and on what schedule? 
	Answer:  Yes, 5% will be withheld from each Application for Payment. 





